## Gantt Chart
Task # | Task | Responsible | Start | End | Duration(Weeks) | time axis 2025-09-15 to 2025-11-24
1 | Requirements Analysis | Jonathon | 2025-09-15 | 2025-09-22 | 1
2 | System Architecture & Initial Codebase | Jonathon | 2025-09-22 | 2025-09-29 | 1
3 | Database Setup & Integration | Zara | 2025-09-29 | 2025-10-13 | 2
4 | Testing Plan Development | Zara | 2025-10-13 | 2025-10-20 | 1
5 | Implementation of Room Check Features | Jonathon | 2025-10-20 | 2025-11-03 | 2
6 | System Testing & Debugging | Zara | 2025-11-03 | 2025-11-10 | 1
7 | Deployment Setup | Jessica | 2025-11-10 | 2025-11-24 | 2
8 | Final Integration & Demonstration | Jessica | 2025-11-24 | 2025-12-01 | 1

## Help
Project Start Date | 2024-01-01
Days Per Column | 7
Instructions
1. Update "Project Start Date" and "Days Per Column" above.
2. Update the gantt chart rows with task names, start dates, and end dates.
3. The template will automatically fill the gantt chart bars.
Provided By
onlinegantt.com - Free Online Gantt Chart Software